## 工作表1
| Due Date | Person Responsible | Task | Test Plan | Dependencies
1 |  |  | Test and characterize components | Test each component and characterize the inputs and outputs | Receiving components
1a | 2019-11-10 | JZ | Evaluate the voltage input of the motor | use multimeter to test the output voltage from the driver | receiving driver
1b | 2019-11-10 | JZ | Evaluate the current input of the motor | use multimeter to test the output current from the driver | receiving driver
1c | 2019-11-10 | OF | Evaluate the output of the ultrasonic sensor | Use Digilent Analog Discovery2 to check the output from sensor | Receiving sensor
1d | 2019-11-10 | TC | Evaluate the motor driver | Check the drivers that Potter has to see if they work (TB6612FNG motor driver Sparkfun) and determine what I/O pins that are needed to be connected to
1e | 2019-11-10 | JZ | test motor | test the motor witht the driver | receiving motor
2 |  |  | Build circuit on a breadboard | Build circuit on a breadboard and verify that it functions as expected. |  | Receiving photosensor
2a | 2019-11-12 | OF | Build a breadboard circuit for the ultrasonic sensor |  | Task 1c
2b | 2019-11-12 | JZ | Build a breadboard circuit for all 3 motors | Connect all 3 together to see if they all work in unison | Task 1a, 1b, 1c, 1e
3 |  |  | Connect breadboard circuit to controller | Test interaction between controller and circuit by using the controller to read inputs and drive outputs.
3a | 2019-11-17 | OF |  | Confirm that the ultrasonic sensor behaves as expected once connected to the microcontoller | Task 2a
3b | 2019-11-17 | OF |  | Test to see if the motors move as planned based off the code compiled on the Atmel board. In other words, test if PWM works on each individual controller and if each motor uses PWM in unison | Test the output voltage of the circuit to ensure that it uses most of the 0-1.8V range.Also test the currents of any pins that will be connected to the controller.
3c | 2019-11-17 | TC | Connnect everything to the microcontroller | Connect the motor driver, motors, and the ultrasonic sensor to the Atmel board. Test to see if it still functions as expected with every component combined. | Task 2c
4 |  |  | Build final circuitry using protoboards or other secure methods
4a | 2019-11-17 | JZ |  | Test the circuit as it was tested in Task 2 and verify that it behaves the same. | Task 2a, 3a
4b | 2019-11-17 | JZ | Build motor circuit on protoboard | Test the circuit as it was tested in Task 2 and verify that it behaves the same. Test each motor individually and then once the motors are all working, then combine all 3 motors to test. | Task 2b, 3b
4c | 2019-11-17 | JZ | Build the motors, motor driver, and ultrasonic sensor on the protoboard | Test the circuit as it was tested in Task 2 and verify that it behaves the same. | Task 2c, 3c
5 |  |  | Connect final circuitry to controller | Test interaction between controller and circuit by using the controller to read inputs and drive outputs. | Task 4
5a | 2019-11-21 | JZ, OF | Connect final ultrasonic sensor circuit to controller | Test interaction between the circuit and the controller as it was tested in Task 3 and verify that it behaves the same. | Task 4a
5b | 2019-11-21 | JZ, OF | Connect final motor circuit to controller | Test interaction between the circuit and the controller as it was tested in Task 3 and verify that it behaves the same. | Task 4b
5c | 2019-11-21 | JZ, OF | Connect final ultrasonic and motor circuit to controller | Test interaction between the circuit and the controller as it was tested in Task 3 and verify that it behaves the same. | Task 4c
5 |  |  | Develop software | Test software at every step.Testing can be performed with breadboard circuit, final circuit, or temporary circuit to simulate the hardware.
5a | 2019-11-28 | JZ, TC | Write code to output to putty console what value ultrasonic sensor is reading | Verify that you the putty console prints expected distance values from the sensor. Connect using breadboard circuit.
5b | 2019-11-28 | OF, TC | Write software to interact with the ultrasensor logic | Verify that the putty console prints what action is expected from the sensor value output. This is the code logic for how the vehichle should move based off the distance detected by the sensor.
5c | 2019-11-28 | OF, TC | Write software to interact with the motors | Verify that each motor individually rotates with basic code. Then test all 3 motors a the same time to ensure all 3 rotate. Connect on a breadboard when testing.
5d | 2019-11-28 | TC | Integrate the motors and the sensor | Verify that the components work together. That the motors rotate and the sensor still behaves as expected. Test on breadboard and then protoboard.
6 |  |  | Integrate final hardware and software | Test the entire system and verify operation | Task 4, 5
6a | 2019-11-28 |  | Connect final hardware to controller and execute software | Verify that the motors move as expected based off the distance that the ultrasonic sensor detects.
6b |  |  |  | Verify that the vehichle conistently behaves as expected. Look for any faults or bugs.
7 |  |  | Build case/packaging/platform for the system | Ensure that all pieces fit and are secured
7a | 2019-11-30 |  | Decide how to package your project.Don't forget to consider how wires are connected, etc. | Discuss the idea with the instructor.
7b | 2019-11-30 |  | Request resources for packaging such as 3D printing or laser cutter or to purchase parts | Discuss this with the instructor.
7c | 2019-11-30 |  | Build the packaging | Ensure that packaging meets desired specs
7d | 2019-11-30 |  | Integrate final hardware solution in to packaging | Ensure that all pieces fit and are secured.Verify that the system operates as expected | Task 5
| on time |  | integrate sensor and motor sooner rather than later
| behind |  | get the chassis built and test the motors on there
very late